## Monthly Activity Log
BA Team – Monthly Activity Log
📋 Fill in one row per activity. All yellow-highlighted columns are mandatory. Select values from the dropdown lists where provided.
# | Month | Team Member | Department / Module | Ticket / Ref No. | Project / Activity Name | Description of Work | Client | Category | Priority | Status | Notes / Blockers
1 | April | Shennaz | SAP SD |  | Aviation Surcharge (ZAVS) | Configured and tested ZAVS pricing condition in QAS. Investigated condition determination and access sequence behaviour. Prepared emergency change documentation and UAT support. | PetroSA | Project | High | Completed
2 | April | Shennaz | SAP MM |  | Contract Expiry Control | Investigated contract expiry controls for PO/SES processing. Performed QAS testing and documented findings for ABAP team. | PetroSA | Incident/Bug Fix | Low | Completed
3 | April | Shennaz | SAP FI |  | Ghana Company Code Project | Reviewed chart of accounts mapping, account groups, number ranges and company code configuration requirements. | PetroSA Ghana | Project | Medium | In Progress
4 | April | Shennaz | SAP FI/TRM |  | Treasury Corrections | Assisted with TBB1/TPM10 treasury postings and correction process analysis. | PetroSA | User Support | Low | Completed
5 | April | Shennaz | SAP SD |  | Credit Exposure Investigation | Analysed customer credit exposure update issue and RVKRED77 behaviour. | PetroSA | Incident/Bug Fix | Low | Completed
6 | April | Shennaz | SAP Travel |  | Travel Management Support | Resolved trip and expense claim issues and provided user support. | SANPC | Incident/Bug Fix | Low | Completed
7 | April | Shennaz | SAP FI |  | Period-End Support | Supported period-end activities including balance carry-forward and account investigations. | PetroSA | Incident/Bug Fix | Low | Completed
8 | April | Shennaz | SAP MM |  | PO Output Notifications | Assisted in Investigated workflow and email notification issues for purchase orders. | PetroSA | Incident/Bug Fix | Low | Completed
9 | April | Nyameka | HR/Payroll | 69585655 | Payslips- October 2025 | Incorrect for SFF due to SARS Bi-Annual. SARS Payment is not aligned to Sage for SANPC. | SANPC | Admin/Config | Low | In Progress
10 | April | Nyameka | HR/Payroll | 69585765 | July Backpay line vs Backpay Overtime line | July Backpay Line to be aligned and removed from Overtime in August 2025 payroll. | SANPC | Admin/Config | Low | In Progress
11 | April | Nyameka | HR/Payroll | 69585703 | EMP 201 Payments Sep to Nov | Payment does not reconcile due to item on Line 5. | SANPC | Admin/Config | Low | In Progress
12 | April | Nyameka | HR/Payroll | 69585655 | October 2025 Payslip Discrepancy | The SARS payment reflected in the October 2025 payslips is not aligned with Sage records for SANPC. | SANPC | Admin/Config | Low | In Progress
13 | April | Nyameka | HR/Payroll | 71880714 | Run Time error | Run time error investigation. | SANPC | Incident/Bug Fix | Low | In Progress
14 | April | Nyameka | SAP HR |  | PetroSA Solidarity Premium Update | PetroSA Solidarity Premium Update. | PetroSA | Admin/Config | Low | Completed
15 | April | Nyameka | SAP HR |  | PetroSA Mortgage Premium Update | PetroSA Mortgage Premium Update. | PetroSA | Admin/Config | Low | Completed
16 | April | Nyameka | SAP HR |  | PetroSA COID Premium Update | PetroSA COID Premium Update. | PetroSA | Admin/Config | Low | Completed
17 | April | Lindiwe | IT | 77317642 | Signing Hub | Signing hub access. | SANPC | Incident/Bug Fix | Low | Completed
18 | April | Lindiwe | IT | 76861404 | BPM - Password Resets | Resetting all BPM/ACCPAC passwords for the users that are using the system. | SANPC | User Support | Low | Completed
19 | April | Lindiwe | IT | Emails | BPM - Business Connect Loading | Loading Business connect, MPLS, Network points, Sage Support PO GRV. | SANPC | User Support | Low | Completed
20 | April | Lindiwe | Finance | Emails | BPM - RCP Investigation | Check where the RCPs are stuck. | SANPC/SFF | Incident/Bug Fix | Low | Completed
21 | April | Lindiwe | IT | Emails | BPM - Req Allocation | Allocating the Reqs to correct approvers. | SANPC | User Support | Low | Completed
22 | April | Lindiwe | IT | Emails | BPM - Transaction Re-allocation | Re-allocate transactions to Sechaba for approval. | SANPC | User Support | Low | Completed
23 | April | Lindiwe | IT | Emails | BPM - Scope of Work Loading | Loading Scope of work for UPS, VMware licenses and Dell laptop Charges. | SANPC | User Support | Low | Completed
24 | April | Lindiwe | IT | 77314897 | QBCON Installation | Installation of QBCON-Plant Maintenance Icon on laptop. | SANPC | User Support | Low | Completed
25 | April | Lindiwe | IT | Emails | BPM - Discard Reqs/POs | Discarding all the Reqs Or POs as per the user's Request. | SANPC | User Support | Low | Completed
26 | April | Lindiwe | IT | Emails | BPM - Grant Access | Granting Access to BPM for Wayne, Comfort Bunting and Azarias. | SANPC | Incident/Bug Fix | Low | Completed
27 | April | Lindiwe | IT | Emails | Signing Hub - Grant Access | Granting Access to Signing hub for Wayne, Comfort Bunting and Azarias. | SANPC | Incident/Bug Fix | Low | Completed
28 | May | T A Willems | IT |  | ISS Upgrade - QAS Server Testing | Encountered issues relating to TempDB and server connectivity. Resolved with assistance from Infrastructure Team. | PetroSA | Project | Medium | Completed
29 | May | T A Willems | IT | Problem:145411 | IIS Tampering - EDI Application Recovery | Investigated IIS Tampering which resulted in EDI Business Application being unavailable for more than 24 hours. Resolved and provided input to Incident Report. | PetroSA | Incident/Bug Fix | High | Completed
30 | May | T A Willems | SAP HR | CRQ: 77012428 | Compensation Statement - Alternate Solution | Developed, tested with End Users and released. Deployed via emergency Change to allow SAP Team more time to investigate long term solution. | PetroSA | Project | High | Completed
31 | May | T A Willems | IT |  | BBEE ESD Stakeholder Database Solution | Initial session conducted with Business Users to understand requirements. Further deliberation required to determine direction. | PetroSA/SANPC | User Support | Low | Pending
32 | May | T A Willems | IT | 52710601 | Procurement Email Tender Mailbox Replacement | Requirement complete, planning complete, currently in development. Ongoing feedback sessions with Business Users. Planned finalisation Mid-June. | PetroSA/SANPC | Project | Medium | In Progress
33 | May | T A Willems | IT |  | ISS Upgrade - Procurement Public Website Update | Development complete, awaiting time from Project Team to confirm SQL Databases/Tables/Views before finalising and sending to CCB for Go Live. | PetroSA | Project | Medium | In Progress
34 | May | T A Willems | IT |  | ISS Production - SQL 2022 Cluster Build | Specifications agreed with Infrastructure, Project Team and Vendor. SQL Server 2022 Cluster build started. To be finalised next week. | PetroSA | Project | Medium | In Progress
35 | May | T A Willems | IT |  | AG Audit Ad-Hoc Support | Ongoing ad-hoc requests for AG Audit queries for Security and Business Applications Team. | PetroSA | User Support | Low | In Progress
36 | May | T A Willems | IT |  | Customer Online Application Relaunch | Requirements sent to Business Users. Redesigned two business applications based on End User feedback. Currently in development. Next session 3 June. | PetroSA | Project | Medium | In Progress
37 | May | T A Willems | IT | Problem: 133172 | ESS Problem Investigation | Issues point to Meraki implemented during SD-WAN. Next step: get assistance from Infrastructure Team and MTN. Issue isolated to remote site access Web Applications in Parow. | PetroSA | Project | Low | In Progress
38 | May | T A Willems | IT |  | Mentoring: Phase 1 | Drafted and discussed plan with Mentee and shared with Line Manager. | SANPC | Mentoring | Low | In Progress
39 | May | T A Willems | IT |  | Apply Screensavers for the Month | 3 Screensavers applied for the month. | PetroSA | Other | Low | Completed
40 | May | T A Willems | IT | 74568700 | SharePoint Well Data Site Investigation | Investigated claimed disappearance of folders. Created Stream Search Views for NVU Team. Resolved issues with Python programs created by NVU Team. | PetroSA | Project | Low | In Progress
41 | May | Mphatheleni Matidze | Business Application | 78078099 | Restore CEF Website | Service was temporarily down due to storage limit reached. | Legacy/CEF | Other | High | Completed
42 | May | Mphatheleni Matidze | Business Application | 77168702 | CSI - Web Pages and Contact Form Creation | Create a CSI overview, Contact, Services Pages. | SANPC | Project | Low | Completed
43 | May | Mphatheleni Matidze | Business Application | 75627621 | Configure/Develop Document Management System | Configure/Develop Document Management System with Reviewers Workflow Using React, SharePoint and Power Automate. | SANPC | Project | Medium | In Progress
44 | May | Mphatheleni Matidze | Business Application | 77148063 | Procurement Shared Drive | Create a SharePoint Drive for PetroSA and SANPC to collaborate and share resources. | SANPC | Project | Low | Completed
45 | May | Mphatheleni Matidze | Business Application | 78079869 | Risk Management System | Assist in development and testing of the Enterprise Risk Management System. | SANPC | Project | Medium | In Progress
46 | May | Mphatheleni Matidze | Business Application | 78080759 | Update and Redeploy CEF Internal Mobile App | The CEF Mobile App required significant updates to accommodate new functional requirements, security enhancements, and updated technology libraries. | Legacy/CEF | Project | Low | In Progress
47 | May | Mphatheleni Matidze | Business Application |  | SANPC Letterhead Update on Intranet | Updated the SANPC letterhead on the Intranet. | SANPC | Admin/Config | Low | Completed
48 | May | Shennaz | SAP SD |  | Pricing Condition Fix | Implemented and tested pricing access sequence changes to resolve incorrect pricing determination. | PetroSA | Project | Low | Completed
49 | May | Shennaz | SAP MM |  | Contract Expiry Enhancement Analysis | Continued analysis of expired contract processing and SES creation behaviour. Coordinated with ABAP and business teams. | PetroSA | Reporting | Low | In Progress
50 | May | Shennaz | SAP FI |  | Ghana Company Code Configuration | Prepared COA upload structure and reviewed configuration readiness for new company code. | PetroSA Ghana | Admin/Config | Low | In Progress
51 | May | Shennaz | SAP MM |  | STO / Workflow Notifications | Investigated notification issues impacting STO and PO related workflows. | PetroSA | Incident/Bug Fix | Low | Completed
52 | May | Shennaz | SAP FI |  | Foreign Currency Vendor Clearing | Analysed and supported vendor clearing and reconciliation requirements. | PetroSA | User Support | Low | Completed
53 | May | Shennaz | SAP PS |  | Project Commitments Analysis | Investigated PR/PO commitment reporting and project system behaviour. | PetroSA | Project | Medium | Completed
54 | May | Shennaz | SAP FI/CO |  | Reporting & Queries | Developed and analysed SAP queries and reports for finance and procurement users. | PetroSA | Project | Medium | In Progress
55 | May | Shennaz | SAP Support |  | General SAP Support | Provided incident resolution, user support, testing, documentation and change management activities. | PetroSA/SANPC | Incident/Bug Fix | Low | Completed
56 | May | Nyameka | HR/Payroll | 69585655 | October 2025 Payslip Discrepancy | The SARS payment reflected in the October 2025 payslips is not aligned with Sage records for SANPC. | SANPC | Admin/Config | Low | Completed
57 | May | Nyameka | HR/Payroll | 76920689 | Shift Roster Configuration on Sage (Saldanha) | Enablement of the shift roster functionality for the Saldanha site on Sage. | SANPC | Admin/Config | Low | In Progress
58 | May | Nyameka | HR/Payroll | 76921191 | Shift Roster Leave Miscalculation | Shift Roster Leave Miscalculating leave days on Sage. | SANPC | Admin/Config | Low | In Progress
59 | May | Nyameka | HR/Payroll | 77901568 | COID Earnings Setup | When processing a COID report for Dept of Labour, the report only processes employees' earnings for three months not the full year. | SANPC | Admin/Config | Low | In Progress
60 | May | Nyameka | HR/Payroll | 76920962 | SARS Submission Support | Assist with SARS Recon. | SANPC | User Support | Low | Completed
61 | May | Nyameka | HR/Payroll | 69585655 | Payslips - October 2025 (SARS) | Incorrect for SFF due to SARS Bi-Annual. SARS Payment is not aligned to Sage for SANPC. | SANPC | Admin/Config | Low | Completed
62 | May | Nyameka | HR/Payroll | 69585765 | July Backpay vs Backpay Overtime | July Backpay Line to be aligned and removed from Overtime in August 2025 payroll. | SANPC | Admin/Config | Low | Completed
63 | May | Nyameka | HR/Payroll | 69585703 | EMP 201 Payments Sep to Nov | Payment does not reconcile due to item on Line 5. | SANPC | Admin/Config | Low | Completed
64 | May | Nyameka | IT | 77459225 | IMS Analytical Report Access | Quality department cannot access the IMS Analytical reports via both LAN and VPN. | PetroSA | Incident/Bug Fix | Low | Completed
65 | May | Nyameka | IT | 77226834 | IMS Reports Issue | IMS tool is not pulling out the analytical reports properly. Incident numbers appearing under title. | PetroSA | Incident/Bug Fix | Low | In Progress
66 | May | Nyameka | IT | 76797458 | Cannot Connect to SAP (Wi-Fi) | User unable to connect to SAP via Wi-Fi intermittently. | PetroSA | User Support | Low | Completed
67 | May | Nyameka | IT | 77626961 | Struggle to Access IMS on SAP | Path to IMS does not open. Stops at launch NWBC. | PetroSA | Project | High | In Progress
68 | May | Nyameka | IT | 77561253 | SAP Log In Error | Cannot log into SAP currently. | PetroSA | Incident/Bug Fix | High | In Progress
69 | May | Nyameka | IT | 77464517 | SAP Login Error (Role/Auth) | Can log into SAP but experiencing errors. | PetroSA | Incident/Bug Fix | Low | In Progress
70 | May | Nyameka | SAP HR |  | Termination of SANPC Employees from PetroSA Structure | Termination of SANPC Employees from PetroSA Structure. | PetroSA | Other | Low | In Progress
71 | May | Nyameka | SAP HR |  | PetroSA PayScale Update | PetroSA PayScale Update. | PetroSA | Admin/Config | Low | In Progress
72 | May | Nyameka | SAP HR |  | PetroSA CEPPAWU Premium Update | PetroSA CEPPAWU Premium Update. | PetroSA | Admin/Config | Low | In Progress
73 | May | Nyameka | SAP HR |  | FA Platform Shift Roster | FA Platform Shift roster configuration. | PetroSA | Admin/Config | Low | Completed
74 | May | Lindiwe | IT | 77317642 | Signing Hub | Signing hub access. | SANPC | Incident/Bug Fix | Low | Completed
75 | May | Lindiwe | IT | 76861404 | BPM - Password Resets | Resetting all BPM/ACCPAC passwords for the users that are using the system. | SANPC | User Support | Low | Completed
76 | May | Lindiwe | IT | Emails | BPM - Business Connect Loading | Loading Business connect, MPLS, Network points, Sage Support PO GRV. | SANPC | User Support | Low | Completed
77 | May | Lindiwe | Finance | Emails | BPM - RCP Investigation | Check where the RCPs are stuck. | SANPC/SFF | Incident/Bug Fix | Low | Completed
78 | May | Lindiwe | IT | Emails | BPM - Req Allocation | Allocating the Reqs to correct approvers. | SANPC | User Support | Low | Completed
79 | May | Lindiwe | IT | Emails | BPM - Transaction Re-allocation | Re-allocate transactions to Sechaba for approval. | SANPC | User Support | Low | Completed
80 | May | Lindiwe | IT | Emails | BPM - Scope of Work Loading | Loading Scope of work for UPS, VMware licenses and Dell laptop Charges. | SANPC | User Support | Low | Completed
81 | May | Lindiwe | IT | 77314897 | QBCON Installation | Installation of QBCON-Plant Maintenance Icon on laptop. | SANPC | User Support | Low | Completed
82 | May | Lindiwe | IT | Emails | BPM - Discard Reqs/POs | Discarding all the Reqs Or POs as per the user's Request. | SANPC | User Support | Low | Completed
83 | May | Lindiwe | IT | Emails | BPM - Grant Access | Granting Access to BPM for Wayne, Comfort Bunting and Azarias. | SANPC | Incident/Bug Fix | Low | Completed
84 | May | Lindiwe | IT | Emails | Signing Hub - Grant Access | Granting Access to Signing hub for Wayne, Comfort Bunting and Azarias. | SANPC | Incident/Bug Fix | Low | Completed

## Summary Dashboard
BA Team – Monthly Summary Dashboard
📊 All figures update automatically when the Monthly Activity Log is populated. Use the Month filter in B4 to view a specific month.
Filter: Month | All
Total Activities |  | Completed |  | In Progress |  | Pending |  | % Completed |  | Active Members
ACTIVITIES PER TEAM MEMBER
Team Member | Total | Completed | In Progress | Pending | % Done
Shennaz
Nyameka
Lindiwe
T A Willems
Mphatheleni Matidze
TOTAL
ACTIVITIES BY CATEGORY | [6 empty] | ACTIVITIES BY CLIENT
Category | Count | % of Total |  |  |  |  | Client | Count | % of Total
Project | [6 empty] | SANPC
Incident/Bug Fix | [6 empty] | PetroSA
Change Request | [6 empty] | PetroSA Ghana
User Support | [6 empty] | Legacy/CEF
Admin/Config | [6 empty] | SANPC/SFF
Reporting | [6 empty] | PetroSA/SANPC
Mentoring | [6 empty] | Other
Other

## Team Member View
BA Team – Team Member Workload View
👤 Select a team member in B3 to filter. Select 'All' to see the full team. Updates automatically from the Monthly Activity Log.
Team Member: | All |  | Month: | All
# | Month | Team Member | Dept/Module | Ticket No. | Activity Name | Description | Client | Category | Priority | Status

## Client Report
BA Team – Activities by Client
📌 Updates automatically from Monthly Activity Log. Use the Month filter to narrow results.
Filter: Month | All
Client | Total | Completed | In Progress | Pending | % Completed | % of All Work | Top Assignee | Top Category | Open Items
SANPC
PetroSA
PetroSA Ghana
Legacy/CEF
SANPC/SFF
PetroSA/SANPC
Other
TOTAL
TEAM MEMBER BREAKDOWN PER CLIENT
SANPC
Team Member | Total | Completed | In Progress | Pending | % Done
Shennaz
Nyameka
Lindiwe
T A Willems
Mphatheleni Matidze
PetroSA
Team Member | Total | Completed | In Progress | Pending | % Done
Shennaz
Nyameka
Lindiwe
T A Willems
Mphatheleni Matidze
PetroSA Ghana
Team Member | Total | Completed | In Progress | Pending | % Done
Shennaz
Nyameka
Lindiwe
T A Willems
Mphatheleni Matidze
Legacy/CEF
Team Member | Total | Completed | In Progress | Pending | % Done
Shennaz
Nyameka
Lindiwe
T A Willems
Mphatheleni Matidze
SANPC/SFF
Team Member | Total | Completed | In Progress | Pending | % Done
Shennaz
Nyameka
Lindiwe
T A Willems
Mphatheleni Matidze
PetroSA/SANPC
Team Member | Total | Completed | In Progress | Pending | % Done
Shennaz
Nyameka
Lindiwe
T A Willems
Mphatheleni Matidze
Other
Team Member | Total | Completed | In Progress | Pending | % Done
Shennaz
Nyameka
Lindiwe
T A Willems
Mphatheleni Matidze
ALL OPEN ITEMS (In Progress & Pending)
Client | Team Member | Ticket No. | Activity Name | Description | Category | Priority | Status | Month | Notes

## Monthly Report
BA Team – Monthly Activity Report
Reporting Month:
Prepared by: | Team Lead
Date Prepared:
1. EXECUTIVE SUMMARY
Total Activities Logged
Completed
In Progress
Pending
Completion Rate
Active Team Members
2. ACTIVITIES BY TEAM MEMBER
Team Member | Total | Completed | In Progress | Pending | % Done
Shennaz
Nyameka
Lindiwe
T A Willems
Mphatheleni Matidze
3. ACTIVITIES BY CATEGORY
Category | Count | % of Total
Project
Incident/Bug Fix
Change Request
User Support
Admin/Config
Reporting
Mentoring
Other
4. ACTIVITIES BY CLIENT
Client | Total | Completed | In Progress | Pending | % Done
SANPC
PetroSA
PetroSA Ghana
Legacy/CEF
SANPC/SFF
PetroSA/SANPC
Other
5. OBSERVATIONS & HIGHLIGHTS
Notable achievements / highlights this month:
Items still in progress – expected completion:
Blocked / Pending items and reasons:
Risks or escalations:
Recommended actions / next steps:

## How To Use
How To Use This Workbook
SHEET | PURPOSE / HOW TO USE
📋 Monthly Activity Log | Team fills in one row per activity every month. Use the dropdown lists in each column. Yellow cells are mandatory. Supports up to 100 activities per load.
📊 Summary Dashboard | Auto-calculates KPIs, team workload, category and client breakdowns from the log. Press Ctrl+Alt+F9 to refresh after updates.
👤 Team Member View | Select a team member from the B3 dropdown to see only their activities. Useful for 1-on-1s and check-ins.
📄 Monthly Report | Auto-populated report template. Fill in the 'Observations' section manually before sharing. Print or export as PDF.
STATUS COLOURS
🟢 Completed | Activity fully done
🟡 In Progress | Work underway
🔴 Pending | Not yet started or blocked
PRIORITY COLOURS
🔴 High | Urgent – needs attention this sprint
🟡 Medium | Normal priority
🟢 Low | Can be deferred if needed